## MU Jaipur ¦ Project Plan
Task Name | Duration | Start | Finish | Reponsible Party | Status | % Complete
Envisioning | 2 days | Fri 7/28/23 | Mon 7/31/23 |  | Complete | 100%
Project Kickoff | 1 day | Fri 7/28/23 | Fri 7/28/23 | Bitscape | Complete | 100%
High Level Project Plan | 1 day | Fri 7/28/23 | Fri 7/28/23 | Bitscape | Complete | 100%
Collect Information and Assessment of Existing ADDS Infrastructure | 1 day | Mon 7/31/23 | Mon 7/31/23 |  | Complete | 100%
Check domain and forest functional level | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Check AD Sites and Services | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Check replication status of domain controllers | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Check List of domains | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Check networking and DNS settings | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Check DNS zones | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Check the web config of DB Server | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Check AD Connect | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Assessmment of Microsoft 365 | 1 day | Mon 7/31/23 | Mon 7/31/23 |  | Complete | 100%
Check domain availability | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape | Complete | 100%
Check the current sync status | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape | Complete | 100%
Check the users list | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape | Complete | 100%
Conduct peer review | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape | Complete | 100%
Develop strategies and plans | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape | Complete | 100%
Identiy goals and objectives | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape & Manipal Jaipur | Complete | 100%
Communication plan | 1 day | Mon 7/31/23 | Mon 7/31/23 | Bitscape | Complete | 100%
Planning | 1 days | Sat 8/5/23 | Mon 8/5/23 |  | Complete | 100%
Setup project envisioning | 1 day | Sat 8/5/23 | Sat 8/5/23 |  | Complete | 100%
Review the current and target environments and identify any potential issues or challenges that may arise during the migration. | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Determine the scope of the migration - IAM, AD Objects (Users, Groups, Service accounts, workstations) need to be migrated. | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Reviewing User/Data Schema | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Define migration strategy | 1 day | Sat 8/5/23 | Sat 8/5/23 |  | Complete | 100%
Plan PDC/ADC server configuration | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Plan networking | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Plan connectivity between on-prem to azure | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Plan AD Connect | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Plan AD Sites and Services | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Document Assumptions | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Define migration pre-requisites | 1 day | Sat 8/5/23 | Sat 8/5/23 |  | Complete | 100%
Identify number of migrations servers based on workloads (AD Objects) | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Finalize the Azure VNET networking (subnet must not overlap with existing network) | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Finalize PDC/ADC servers (Naming convention, SKU, Size, Domain/Forest) | 1 day | Sat 8/5/23 | Sat 8/5/23 | Bitscape | Complete | 100%
Configuration and Execution | 5 days | Mon 8/7/23 | Fri 8/11/23 |  | Future Task | 0%
Setup Azure Virtual Network | 1 day | Mon 8/7/23 | Mon 8/7/23 |  | Future Task | 0%
Configure virtual network for PDC | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape & Manipal Jaipur | Complete | 0%
Configure required subnets | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape & Manipal Jaipur | Complete | 0%
Configure connectivity between on-prem to Azure | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape & Manipal Jaipur | Complete | 0%
Validate connectivity | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape & Manipal Jaipur | Complete | 0%
Setup PDC/ADC servers | 1 day | Mon 8/7/23 | Mon 8/7/23 |  | Future Task | 0%
Deploy PDC server in Azure | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape | Complete | 0%
Deploy ADC servers in on-prem | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape | Complete | 0%
Deploy AD Connect server | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape | Complete | 0%
Validate deployment | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape & Manipal Jaipur | Complete | 0%
Validate replication between domain controllers | 1 day | Mon 8/7/23 | Mon 8/7/23 | Bitscape | Complete | 0%
Configure Domain Controller Pre-requisites | 1 day | Tue 8/8/23 | Tue 8/8/23 |  | Future Task | 0%
Configure ADDS role in PDC/ADC servers | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape & Manipal Jaipur | Complete | 0%
Configure DNS role into the PDC | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Complete | 0%
Configure DNS zone in PDC | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Complete | 0%
Configure Conditional forwarder on Both DCs (Source and Target) | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Future Task | 0%
Configure forest trust relationship between source and target domain | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Future Task | 0%
Configure DNS settings on source and target domain controller | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Future Task | 0%
Trust validation on source and target domain controller | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Future Task | 0%
Configuration od DNS suffix search list on source and target domain controller using GPO | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Future Task | 0%
Validation of DNS suffix search list | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Future Task | 0%
Disbale the local Firewall using GPO | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Future Task | 0%
Add admin account to administrator group using GPO | 1 day | Tue 8/8/23 | Tue 8/8/23 | Bitscape | Future Task | 0%
Manually creation of OU structure on target DC | 1 day | Tue 8/8/23 | Tue 8/8/23 | Manipal jaipur | Future Task | 0%
Setup additional servers (Count 18) | 3 day | Wed 8/9/23 | Fri 8/11/23 |  | Future Task | 0%
Deploy 9 additional servers in source domain | 1 day | Wed 8/9/23 | Wed 8/9/23 | Bitscape | Complete | 0%
Deploy 9 additional servers in target domain | 1 day | Wed 8/9/23 | Wed 8/9/23 | Bitscape | Complete | 0%
Promote additional servers as ADC | 1 day | Thu 8/10/23 | Thu 8/10/23 | Bitscape & Manipal Jaipur | Complete | 0%
Configure Pre-requisites for migration | 1 day | Fri 8/11/23 | Fri 8/11/23 | Bitscape | Future Task | 0%
Migration (Pilot) | 3 days | Wed 8/16/23 | Fri 8/18/23 |  | Future Task | 0%
Identify and finalize pilot entities (Users, Groups, Service Accounts, Workstations) | 1 day | Wed 8/16/23 | Wed 8/16/23 | Manipal jaipur | Future Task | 0%
Execute AD Connect sync for scoped Pilot entities | 1 day | Wed 8/16/23 | Wed 8/16/23 | Bitscape | Future Task | 0%
Execute Migration for pilot entities (users, groups, workstations, associated profiles) | 2 days | Thu 8/17/23 | Fri 8/18/23 | Bitscape | Future Task | 0%
Validate migrated entities and perform metadata verfication | 1 day | Fri 8/18/23 | Fri 8/18/23 | Bitscape & Manipal Jaipur | Future Task | 0%
Export/Import AD User proxy address from source to target domain | 1 day | Fri 8/18/23 | Fri 8/18/23 | Bitscape | Future Task | 0%
PowerShell - Modify migrated user account properties to match existing configuration (For eg. Password Expiry, Password change) | 1 day | Fri 8/18/23 | Fri 8/18/23 | Bitscape | Future Task | 0%
Migration (Production) | 12 days | Mon 8/21/23 | Wed 9/6/23 |  | Future Task | 0%
Identify and finalize entities (Users, Groups, Service Accounts, Workstations) | 1 day | Mon 8/21/23 | Mon 8/21/23 | Manipal jaipur | Future Task | 0%
Execute AD Connect sync for scoped entities | 1 day | Mon 8/21/23 | Mon 8/21/23 | Bitscape | Future Task | 0%
Execute Migration for entities (users, groups, workstations, associated profiles) | 10 days | Tue 8/22/23 | Tue 9/5/23 | Bitscape | Future Task | 0%
Validate migrated entities and perform metadata verfication | 1 day | Tue 9/5/23 | Tue 9/5/23 | Bitscape & Manipal Jaipur | Future Task | 0%
Export/Import AD User proxy address from source to target domain | 1 day | Tue 9/5/23 | Tue 9/5/23 | Bitscape | Future Task | 0%
PowerShell - Modify migrated user account properties to match existing configuration (For eg. Password Expiry, Password change) | 1 day | Tue 9/5/23 | Tue 9/5/23 | Bitscape | Future Task | 0%
Create VLANs and Sites in AD Sites and Services | 1 day | Wed 9/6/23 | Wed 9/6/23 | Bitscape | Future Task | 0%
Manage | 4 day | Fri 9/8/23 | Wed 9/13/23 |  | Future Task | 0%
Post-Migration activities | 1 day | Fri 9/8/23 | Fri 9/8/23 |  | Future Task | 0%
Post configuration supprt | 4 day | Fri 9/8/23 | Wed 9/13/23 | Bitscape | Future Task | 0%
Provide on-going support and knowledge transfer | 4 day | Fri 9/8/23 | Wed 9/13/23 | Bitscape | Future Task | 0%
Monitor the new environment for any poerformance issues | 4 day | Fri 9/8/23 | Wed 9/13/23 | Bitscape | Future Task | 0%
Summerrize project result | 1 day | Fri 9/8/23 | Fri 9/8/23 | Bitscape | Future Task | 0%
Validation of AD Connect | 1 day | Fri 9/8/23 | Fri 9/8/23 | Bitscape | Future Task | 0%
Validation of AD User and Password sync with Microsoft 365 | 1 day | Fri 9/8/23 | Fri 9/8/23 | Bitscape | Future Task | 0%
Validation of AD Sites and Services | 1 day | Fri 9/8/23 | Fri 9/8/23 | Bitscape | Future Task | 0%
Decommission of additional servers (Count 18) | 3 day | Mon 9/11/23 | Wed 9/13/23 | Bitscape & Manipal Jaipur | Future Task | 0%
Cleanup AD Sites and Services | 3 day | Mon 9/11/23 | Wed 9/13/23 | Bitscape | Future Task | 0%
Post migration resource cleanup | 3 day | Mon 9/11/23 | Wed 9/13/23 | Bitscape | Future Task | 0%
DNS Check - Primary and Secondary | 1 day | Wed 9/13/23 | Wed 9/13/23 | Bitscape | Future Task | 0%
Validation of AD Replication | 1 day | Wed 9/13/23 | Wed 9/13/23 | Bitscape | Future Task | 0%

## Escalation Matrix
Role/Title | Name | Contact Number | Email ID | Escalation Channel
Systems Engineer | Ishan Kansara | 992525 1666 | Ishan.Kansara@bitscape.com | 1st Level
Systems Engineer | Kartikey Khatri | 81282 16016 | kartikey.khatri@bitscape.com
Project Lead / SPOC | Nilesh Kalal | 81284 52250 | Nilesh.kalal@bitscape.com | 2nd Level
Practice Lead | Husain Paliwala | 971460 0135 | husain.paliwala@bitscape.com | 3rd Level
Bitscape CTO | Hirnav Patel |  | Hirnav.Patel@bitscape.com | 4th Level